## Product Backlog
User Story Title | Value Statement | Value | Estimate (Story Points) | Sprint
Choose account to deposit | As a user of banking app, I want to be able to choose the account on which I make a deposit, so that i can make deposits for different particular accounts. | $$$ | 13 | Current Sprint
Enter deposit amount and currency | As a banking app user, I want to be able to enter the deposit amount and currency before making a deposit, so that I can choose how much money I wanna deposit and in which currency. | $$$ | 8 | Current Sprint
View transaction limits within your account | As a banking app user, I want to view transaction limits for my account, so that I can know what are financial limits of my account and how much money I can deposit . | $$$ | 8 | Current Sprint
Confirm deposit | As a banking app user, I want to be able to confirm a deposit before it's made, so that I can avoid a deposit made by mistake or missclick. | $$ | 5 | Next Sprint
Cancel Deposit | As a banking app user, I want to cancel deposit, so that I can overdue it in the case I changed my mind or I want to change the deposit details. | $$ | 5 | Next Sprint
Confirmation Message of deposit | As a banking app user, I want to receive a confirmation message, so that I can be sure that my deposit has been performed. | $$ | 3 | Next Sprint
Enter login and password for account creation | As a banking app user, I want to register an account using login and password, so I will be able to use the app and have a secured account by a password. | $$ | 5 | Next Sprint
Enter email for your account creation | As a banking app user, I want to be able to enter an email for my account, so that I will be able to restore it using my email and it will have an additional security. | $ | 2 | Next Sprint
Confirm account creation and validation | As a banking app user, I want to confirm account creation and validation, so that I will have the possibility to confirm its creation. | $ | 1 | Next Sprint
Receive a confirmation message on email/phone number | As a banking app user, I want to receive a message on email or phone number, so that I will know that my account was saved in the system and I can use it. | $$ | 5 | Next Sprint
Choose account to access | As a banking app user, I want to be able to choose the account which I wanna access, so that I will have the possibility to access a particular account and switch between them. | $ | 3 | Next Sprint
Check balance before a transaction | As a banking app user, I want to check balance before a transaction, so that I can check my financial possibilities before a transaction and evaluate my balance. | $$ | 2 | Next Sprint
See current transactions | As a banking app user, I want to see my current transactions, so that I can know which transactions are performed at the moment and I can manage my finances. | $$ | 5 | Next Sprint
Open a new account with a different currency | As a banking app user, I want to be able to open a new account, so that I can create an account with a different currency or manage my balance by making different type of transactions on it. | $$ | 8 | Next Sprint

## Sprint Backlog
User Story Title | Value Statement | Acceptance Criteria | Value | Estimate (Story Points) | Current Sprint | Sprints
Choose account to deposit | As a user of banking app, I want to be able to choose the account on which I make a deposit, so that i can make deposits for different particular accounts. | Given that I am a in role of a logged-in app user When I open the deposit page Then the system shows me the deposit page When I choose an account to make a deposit the app requires the account details When I fill all the required fields Then the system allows me to make a deposit on that account | $$$ | 13 | Current Sprint | Name | Current Sprint | Next Sprint
Enter deposit amount and currency | As a banking app user, I want to be able to enter the deposit amount and currency before making a deposit, so that I can choose how much money I wanna deposit and in which currency. | Given that I am a in role of a logged-in app user When I open the deposit page Then the system shows me the deposit page When I choose an account to make a deposit the app requires the account details When I fill all the required fields Then the app requires to enter the deposit amount and currency When I enter the deposit amount and current and press submit a deposit Then the system makes my deposit | $$$ | 8 | Current Sprint | Start date | 2021-03-21 | 2021-04-04
View transactions limits within your account | As a banking app user, I want to view transaction limits for my account, so that I can know what are financial limits of my account and how much money I can deposit . | Given that I am in the role of a logged-in user When I open the account details Then the system shows me different account details by category When I choose the transaction limits of my account from account details categories Then the system shows me what are transaction limits of my account | $$$ | 8 | Current Sprint | End date | 2021-04-01 | 2021-04-15
[6 empty] | Point Capacity | 29 | 29
[6 empty] | Points Assigned | 29 | 29
[6 empty] | Value Attributed | 9 | 12